## Sheet1
Project Name | Foxtrot
Start Date | 2025-08-20
End Date | 2025-09-21
Overall Progress | 100%
Tasks | Responsible | Start | End | Days | Status | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21
Planning
Kick-off meeting | All | 2025-08-20 | 2025-08-21 | 1 | Complete
Project Plan | All | 2025-08-20 | 2025-09-21 | 32 | Complete
Initiation
Design UMLs | Mauritz, Luca | 2025-08-20 | 2025-08-23 | 3 | Complete
Agree on objectives | All | 2025-08-23 | 2025-08-24 | 1 | Complete
ProjectReport | Björn, Silas | 2025-08-20 | 2025-09-21 | 32 | Complete
Development
Game Status Model | Mauritz, Sean | 2025-08-25 | 2025-08-30 | 6 | Complete
MazeGameProtocol | Sean | 2025-08-30 | 2025-09-04 | 6 | Complete
CommandHandler | Silas, Luca | 374619 | 2025-09-05 | 5 | Complete
MazeClientUI | Mauritz, Sean | 2025-09-05 | 2025-09-17 | 12 | Complete
Robot Strategy | Björn | 2025-09-06 | 2025-09-18 | 12 | Complete
Testing | All | 2025-09-18 | 2025-09-20 | 3 | Complete
Operations
Final Configuration | Björn, Silas | 2025-09-18 | 2025-09-20 | 3 | Complete
System Testing | Björn, Silas | 2025-09-18 | 2025-09-20 | 3 | Complete
Launch